## Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project definition |  | 29 | 30 | -1 | 1 |  |  |  | 103.4%
1.1 | Project formulation | everyone | 5 | 5 | 0 | 1 | 2024-12-16 | 2024-12-16 | 1 | 100% | bar: WEEK 1 M; WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
1.2 | Requirement gathering | everyone | 3 | 3 | 0 | 1 | 2024-12-16 | 2024-12-16 | 1 | 100% | bar: WEEK 1 M; WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
1.3 | Technical sketching | everyone | 4 | 4 | 0 | 1 | 2024-12-17 | 2024-12-18 | 2 | 100% | bar: WEEK 1 T to WEEK 1 W; WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
1.4 | User stories writing | everyone | 3 | 3 | 0 | 1 | 2024-12-19 | 2024-12-19 | 1 | 100% | bar: WEEK 1 R; WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
1.5 | Mockups creation | Linda Labonia | 4 | 4 | 0 | 1 | 2025-01-07 | 2025-01-08 | 2 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
1.6 | Function point & CoCoMo estimation | Linda Labonia | 5 | 6 | -1 | 1 | 2025-01-07 | 2025-01-08 | 2 | 120% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
1.7 | Documentation | everyone | 5 | 5 | 0 | 1 | 2025-01-08 | 2025-01-09 | 2 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
2 | Backend & infrastructure |  | 40 | 39 | 1 | 2 |  |  |  | 97.5%
2.1 | Setup PostgreSQL container | Francesco Sidella | 5 | 6 | -1 | 2 | 2025-08-01 | 2025-08-01 | 1 | 120% | bar: WEEK 2 T to WEEK 2 R; WEEK 3 F; WEEK 8 M to WEEK 8 R
2.2 | Create initial tables & seed data | Francesco Sidella & Linda Labonia | 8 | 7 | 1 | 2 | 2025-08-04 | 2025-08-05 | 2 | 87.5% | bar: WEEK 2 T to WEEK 2 R; WEEK 4 M to WEEK 4 T; WEEK 8 M to WEEK 8 R
2.3 | Build DB API skeleton | Francesco Sidella | 9 | 8 | 1 | 2 | 2025-08-06 | 2025-08-11 | 6 | 88.89% | bar: WEEK 2 T to WEEK 2 R; WEEK 4 W to WEEK 5 F; WEEK 8 M to WEEK 8 R
2.4 | Implement user register/login | Giovanni Canedoli | 8 | 9 | -1 | 2 | 2025-08-07 | 2025-08-12 | 6 | 112.5% | bar: WEEK 2 T to WEEK 2 R; WEEK 4 R to WEEK 5 F; WEEK 8 M to WEEK 8 R
2.5 | Implement product list/detail | Giovanni Canedoli | 7 | 7 | 0 | 2 | 2025-08-13 | 2025-08-14 | 2 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
2.6 | Setup env | Francesco Sidella | 3 | 2 | 1 | 2 | 2025-08-15 | 2025-08-15 | 1 | 66.67% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
3 | Customer side |  | 51 | 48 | 3 | 3 |  |  |  | 94.12%
3.1 | Setup customer container | Linda Labonia | 4 | 3 | 1 | 3 | 2025-08-18 | 2025-08-18 | 1 | 75% | bar: WEEK 2 T to WEEK 2 R; WEEK 5 M to WEEK 6 M; WEEK 8 M to WEEK 8 R
3.2 | Build register/login pages | Giovanni Canedoli | 8 | 8 | 0 | 3 | 2025-08-19 | 2025-08-20 | 2 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 6 T to WEEK 6 W; WEEK 8 M to WEEK 8 R
3.3 | Build password recovery page | Francesco Sidella & Giovanni Canedoli | 7 | 7 | 0 | 3 | 2025-08-20 | 2025-08-20 | 1 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 6 W; WEEK 8 M to WEEK 8 R
3.4 | Implement product catalog page | Giovanni Canedoli | 8 | 8 | 0 | 3 | 2025-08-21 | 2025-08-22 | 2 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 6 R to WEEK 6 F; WEEK 8 M to WEEK 8 R
3.5 | Add like feature | Giovanni Canedoli | 7 | 6 | 1 | 3 | 2025-08-25 | 2025-08-25 | 1 | 85.71% | bar: WEEK 2 T to WEEK 2 R; WEEK 7 M; WEEK 8 M to WEEK 8 R
3.6 | Add comments feature | Francesco Sidella | 7 | 7 | 0 | 3 | 2025-08-26 | 2025-08-26 | 1 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 7 T; WEEK 8 M to WEEK 8 R
3.7 | Build cart feature | Francesco Sidella | 7 | 6 | 1 | 3 | 2025-08-26 | 2025-08-27 | 2 | 85.71% | bar: WEEK 2 T to WEEK 2 R; WEEK 7 T to WEEK 7 W; WEEK 8 M to WEEK 8 R
3.8 | Run test | everyone | 3 | 3 | 0 | 3 | 2025-08-27 | 2025-08-27 | 1 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 7 W; WEEK 8 M to WEEK 8 R
4 | Business side |  | 39 | 40 | -1 | 4 |  |  |  | 102.6%
4.1 | Setup business container | Linda Labonia | 4 | 4 | 0 | 4 | 2025-08-28 | 2025-08-28 | 1 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 7 R; WEEK 8 M to WEEK 8 R
4.2 | Build register/login pages | Giovanni Canedoli | 5 | 5 | 0 | 4 | 2025-08-28 | 2025-08-29 | 2 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 7 R to WEEK 8 R
4.3 | Build password recovery page | Giovanni Canedoli | 5 | 5 | 0 | 4 | 2025-09-01 | 2025-09-01 | 1 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
4.4 | Build catalog add page | Francesco Sidella | 8 | 8 | 0 | 4 | 2025-09-02 | 2025-09-02 | 1 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
4.5 | Build catalog modify page | Francesco Sidella & Linda Labonia | 8 | 9 | -1 | 4 | 2025-09-02 | 2025-09-03 | 2 | 112.5% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
4.6 | Build orders view page | Francesco Sidella | 6 | 6 | 0 | 4 | 2025-09-03 | 2025-09-03 | 1 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
4.7 | Run test | everyone | 3 | 3 | 0 | 4 | 2025-09-04 | 2025-09-04 | 1 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R
5 | Integration & deployment |  | 23 | 25 | -2 | 5 |  |  |  | 108.7%
5.1 | Final docker-compose setup | everyone | 8 | 8 | 0 | 5 | 2025-09-08 | 2025-09-09 | 2 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R; WEEK 9 M to WEEK 9 T
5.2 | Configure SMTP service | everyone | 7 | 7 | 0 | 5 | 2025-09-10 | 2025-09-10 | 1 | 100% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R; WEEK 9 W
5.3 | Run integration test | everyone | 8 | 10 | -2 | 5 | 2025-09-11 | 2025-09-12 | 2 | 125% | bar: WEEK 2 T to WEEK 2 R; WEEK 8 M to WEEK 8 R; WEEK 9 R to WEEK 9 F
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 185 | 189 | -4 | 60 | 3.0833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 185 | 181.9167 | 178.8333 | 175.75 | 172.6667 | 169.5833 | 166.5 | 163.4167 | 160.3333 | 157.25 | 154.1667 | 151.0833 | 148 | 144.9167 | 141.8333 | 138.75 | 135.6667 | 132.5833 | 129.5 | 126.4167 | 123.3333 | 120.25 | 117.1667 | 114.0833 | 111 | 107.9167 | 104.8333 | 101.75 | 98.6667 | 95.5833 | 92.5 | 89.4167 | 86.3333 | 83.25 | 80.1667 | 77.0833 | 74 | 70.9167 | 67.8333 | 64.75 | 61.6667 | 58.5833 | 55.5 | 52.4167 | 49.3333 | 46.25 | 43.1667 | 40.0833 | 37 | 33.9167 | 30.8333 | 27.75 | 24.6667 | 21.5833 | 18.5 | 15.4167 | 12.3333 | 9.25 | 6.1667 | 3.0833
[10 empty] | ESTIMATE | 185 | 177 | 175 | 173 | 170 | 170 | 170 | 165 | 160 | 155 | 155 | 155 | 155 | 155 | 155 | 149 | 145 | 142 | 139 | 135 | 131 | 128 | 125 | 122 | 118 | 116 | 113 | 106 | 98 | 94 | 90 | 84 | 77 | 71 | 66 | 62 | 57 | 49 | 43 | 40 | 40 | 36 | 32 | 25 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5353
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 8 | 2 | 2 | 3 |  |  | 5 | 5 | 5 | [5 empty] | 6 | 4 | 3 | 3 | 4 | 4 | 3 | 3 | 3 | 4 | 2 | 3 | 7 | 8 | 4 | 4 | 6 | 7 | 6 | 5 | 4 | 5 | 8 | 6 | 3 |  | 4 | 4 | 7 | 5 | 5 | [15 empty] | 170
[10 empty] | HRS REMAINING | 177 | 175 | 173 | 170 | 170 | 170 | 165 | 160 | 155 | 155 | 155 | 155 | 155 | 155 | 149 | 145 | 142 | 139 | 135 | 131 | 128 | 125 | 122 | 118 | 116 | 113 | 106 | 98 | 94 | 90 | 84 | 77 | 71 | 66 | 62 | 57 | 49 | 43 | 40 | 40 | 36 | 32 | 25 | 20 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 5183

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
1-High | 3 | Customer Authentication | Register | As a Customer, I want to register, so that I can create my profile | Everyone | 8 | Completed |  | Not Started | 1
1-High | 3 |  | Login | As a Customer, I want to login, so that I can access the service | Everyone | 8 | Completed |  | In Progress | 2
2-Med | 3 |  | Logout | As a Customer, I want to logout, so that I can end my session securely | Everyone | 4 | Completed |  | Completed | 4
2-Med | 3 |  | Recover password | As a Customer, I want to recover my password, so that I can regain access to my account | Everyone | 8 | Completed |  |  | 8
1-High | 3 | Customer Product Catalog | View all products | As a Customer, I want to view all available products, so that I can choose what to buy | Everyone | 4 | Completed |  |  | 16
2-Med | 3 |  | View product details | As a Customer, I want to view product details, so that I can evaluate them before buying | Everyone | 4 | Completed |  |  | 24
1-High | 3 | Customer Social Features | Like product | As a Customer, I want to like a product, so that I can express my preference | Everyone | 4 | Completed |  |  | 40
2-Med | 3 |  | Unlike product | As a Customer, I want to unlike a product, so that I can change my mind | Everyone | 4 | Completed |  |  | 80
3-Med | 3 |  | View liked products | As a Customer, I want to view the list of liked products, so that I can access them quickly | Everyone | 2 | Completed
2-Med | 3 |  | Comment on product | As a Customer, I want to comment on a product, so that I can share my opinion | Everyone | 4 | Completed
2-Med | 3 |  | View comments | As a Customer, I want to view product comments, so that I can read other users’ feedback | Everyone | 8 | Completed
1-High | 3 | Customer Shopping Cart | Add to cart | As a Customer, I want to add products to my cart, so that I can prepare for checkout | Everyone | 2 | Completed
1-High | 3 |  | Remove from cart | As a Customer, I want to remove products from my cart, so that I can adjust my order | Everyone | 2 | Completed
2-Med | 3 |  | View cart | As a Customer, I want to view all products in my cart, so that I can review my selection | Everyone | 2 | Completed
1-High | 3 |  | Select quantity | As a Customer, I want to select the quantity of each product in my cart, so that I can customize my purchase | Everyone | 4 | Completed
1-High | 3 |  | Submit cart | As a Customer, I want to submit my cart, so that I can place an order | Everyone | 4 | Completed
1-High | 3 |  | Receive confirmation | As a Customer, I want to receive a confirmation message when the order is placed, so that I know it was successful | Everyone | 1 | Completed
2-Med | 3 |  | Receive error message | As a Customer, I want to receive an error message if the requested quantity is not available, so that I can adjust my cart | Everyone | 1 | Completed
1-High | 4 | Supermarket Authentication | Register | As a Supermarket, I want to register, so that I can create my business account | Everyone | 4 | Completed
1-High | 4 |  | Login | As a Supermarket, I want to login, so that I can manage my catalog and orders | Everyone | 4 | Completed
2-Med | 4 |  | Logout | As a Supermarket, I want to logout, so that I can end my session securely | Everyone | 2 | Completed
2-Med | 4 |  | Recover password | As a Supermarket, I want to recover my password, so that I can regain access to my account | Everyone | 4 | Completed
1-High | 4 | Supermarket Product Catalog | Add products | As a Supermarket, I want to add new products, so that I can expand my catalog | Everyone | 8 | Completed
1-High | 4 |  | View products | As a Supermarket, I want to view the list of all products offered across the platform, so that I can compare my catalog with competitors | Everyone | 2 | Completed
1-High | 4 |  | Update product details | As a Supermarket, I want to update the details of my products so that the catalog is always accurate | Everyone | 8 | Completed
1-High | 4 |  | Update prduct quantity | As a Supermarket, I want to update only the quantity of a product, so that stock levels are kept accurate | Everyone | 4 | Completed
1-High | 4 | Supermarket Orders | View orders | As a Supermarket, I want to view received orders, so that I can process them | Everyone | 8 | Completed

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES
AS A | I WANT TO | SO THAT I CAN | ADDED BY | DATED ADDED
Customer | register | create my profile | everyone | 2024-12-19
Customer | login | access the service | everyone | 2024-12-19
Customer | logout | end my session securely | everyone | 2024-12-19
Customer | recover my password | regain access to my account | everyone | 2024-12-19
Customer | view all available products | choose what to buy | everyone | 2024-12-19
Customer | view product details | evaluate them before buying | everyone | 2024-12-19
Customer | like a product | express my preference | everyone | 2024-12-19
Customer | unlike a product | change my mind | everyone | 2024-12-19
Customer | view the list of liked products | access them quickly | everyone | 2024-12-19
Customer | comment on a product | share my opinion | everyone | 2024-12-19
Customer | view product comments | read other users’ feedback | everyone | 2024-12-19
Customer | add products to my cart | prepare for checkout | everyone | 2024-12-19
Customer | remove products from my cart | adjust my order | everyone | 2024-12-19
Customer | view all products in my cart | review my selection | everyone | 2024-12-19
Customer | select the quantity of each product in my cart | customize my purchase | everyone | 2024-12-19
Customer | submit my cart | place an order | everyone | 2024-12-19
Customer | receive a confirmation message when the order is placed | know it was successful | everyone | 2024-12-19
Customer | receive an error message if the requested quantity is not available | adjust my cart | everyone | 2024-12-19
Supermarket | register | create my business account | everyone | 2024-12-19
Supermarket | login | manage my catalog and orders | everyone | 2024-12-19
Supermarket | logout | end my session securely | everyone | 2024-12-19
Supermarket | recover my password | regain access to my account | everyone | 2024-12-19
Supermarket | add new products | expand my catalog | everyone | 2024-12-19
Supermarket | view the list of all products offered across the platform | compare my catalog with competitors | everyone | 2024-12-19
Supermarket | view received orders | process them | everyone | 2024-12-19
Supermarket | update the details of my products | the catalog is always accurate | everyone | 2024-12-19
Supermarket | update only the quantity of a product | the stock levels are kept accurate | everyone | 2024-12-19